Terms of Reference

Consultancy service (s) for

Haiphong city Resilient to Climate Change and Disaster Risks (HRCD) project

Assignment #1: Training of trainers (ToT) on Community-based Disaster Risk Management – Climate Change Adaptation (CBDRM/CCA) and Hazard-Vulnerability – Capacity Assessment (HVCA) for local partners at district and commune levels and community

Assignment #2: ToT training for teachers/education staff on Child-focused Disaster Risk Reduction – Climate Change Adaptation (CF DRR-CCA)

Assignment #3: Researches on the existing status of Small and Medium Enterprises (SMEs) in three districts towards DRR-CCA, training need assessment and Corporate Social Responsibilities (CSR); to design and deliver the training to SMEs and related institutions.

Assignment #4: Studies on adaptive livelihood options

- Background

Located within the belt of tropical monsoons of Asia and adjoining the Eastern Sea, Hai Phong is under monsoon influence, attracting 31% of the storms and typhoons in Vietnam annually. Hai Phong is susceptible to many disasters such as typhoons, storms, storm surges, high tidal waves, floods, saltwater intrusion, droughts, hails and cold weather. Annually, there are 3-5 storms occurring within the period from June to September. Sharing from the local showed that there have been significant changes in frequency, magnitude and intensity of natural disaster hazards during current years, resulting bad effects to the living environment as well as livelihood of the local people in Hai Phong. Observation from Hon Dau Gauging Station (Do Son, Hai Phong) showed many climate change’s evidences such as changes in temperature, rainfall precipitation, cold fronts, sea level, weather extreme events...); it was recorded that the sea rose by approximately 20 mm during the past 50 years (MONRE, the National Target to Respond to Climate Change, 2008). Sea level rises have resulted in increased erosion and flooding, causing heavy loss and damages for the local people as well as natural resources along coastal areas.  Within the year of 2012, Hai Phong experienced 8 typhoons and in one typhoon, 5 people were killed with a total loss of property of 1,000 billion VND (around 47 million USD).

Taking into account the effects caused by climate change and weather extreme events to the localities, Hai Phong local authorities and people have been trying many measures, including both structural and non-structural ones with focus on enhancing forecasting systems, identifying and mapping the areas with high risks of inundation, SLR, salinity intrusion, land erosion... for land mastering and planning; developing sea dyke systems, development and protection of mangrove forest; treating solid waste, promoting environment protection; raising awareness on climate change to mobilize different population groups to participate in responding.  On 14 Aug., 2013 Hai Phong People Committee released the Plan of Action for Implementation (No.5935/KH-UBND) of the CBDRM Program for the period of 2013-2015.

Besides, as the city has been growing at a fast speed, there has been high density of SMEs and enterprises, contributing significantly to the city’s job creation, socio-economic development process; however, the role and participation of the SMEs in DRR-CCA has not yet been taken into consideration thoroughly either by SMEs themselves or local authorities. The “Hai Phong City Resilient to Climate Change and Disaster Risks (HRCD) project has been designed, taking into consideration all the factors mentioned above. The Project with a lifespan of around three and a half years (tentatively from the third quarter of FY14 until the end of FY17) will be implemented in eight selected communes of Ngo Quyen, Cat Hai and Tien Lang districts. The overall goal of the project is “to increase community resilience of the local people in Hai Phong city vulnerable to natural disaster risks and climate change’s effects”. The project will focus on building DRR and CCA capacity for children, SMEs and communities in the selected areas of Hai Phong city in a comprehensive manner through raising awareness on disaster risks and climate change, increasing local capacity to respond to disaster risks, improving livelihood opportunities as well as reducing vulnerabilities and risks to their livelihoods and the small business sector in target communities.

The outcomes and outputs of the project as follows:

Outcome 1	Building Public-Private Partnership (PPP) in DRR-CCA

Output 1.1	Raise awareness and support for the application of the DRR-CCA best practices for SMEs in the target areas of Ngo Quyen, Tien Lang and Cat Hai districts)

Output 1.2	Support for the enforcement of national policies on PPP in DRR-CCA

Output 1.3	Promote SMEs’ Corporate Social Responsibility (CSR) in DRR-CCA linked to mitigation efforts and environmental protection for SMEs such as clean energy production, CO2 reductions and environmental protection.

Outcome 2	Promote CBDRR and CCA

Output 2. 1	Promote CF DRR – CCA at primary and secondary schools.

Output 2. 2	Promote integration of DRR-CCA into socio-economic development planning through introducing and promoting application of HVCA as well as CDRI in planning exercises; promoting application of disaster –resistant building codes, sustainable use of natural resources etc.

Output 2. 3	Build preparedness and response capacity for local communities of 8 communes/towns

Output 2. 4	Introduction of and support in implementing alternative sustainable livelihood options

- Consultancy assignments

Assignment #1:

To design and deliver Training of trainers (ToT) training on Community-based Disaster Risk Management – Climate Change Adaptation (CBDRM/CCA) and Hazard-Vulnerability – Capacity Assessment (HVCA) for local partners at district/commune level and community; to lead HVCA process with selected trainees including measurement of Climate Disaster Risk Index (CDRI or five dimensions of resilience, namely, physical, social, economic, institutional, and natural) in the project communes.

Expected outcomes of this assignment are at two fold as follows:

Firstly, this activity aims at enhancing capacity for key stakeholders to facilitate DRR-CC activities at lower levels (link with the Government's CBDRM Programme – 1002).

Secondly, it is expected that by the end of this exercise, main disaster risks, vulnerabilities and capacities in the target communes can be identified and documented (via community ‘s disaster profile, hazard maps, disaster seasonal calendars, most vulnerable groups (children, people with disability, the aged, seasonal fishing communities…), livelihood activities [current and potential/alternative], messages for risk communication [via billboards, posters, pano…], early warning systems…Outcomes from HVCA exercise (s) will provide suggestions and hints for what types of DRR-CCA activities/supports/strategies should be applied for specific community, target groups, rapid response teams; methodologies etc. This also links with supporting community in preparing annual community disaster preparedness plan (CDPP)…

(i) Hazard maps at commune/village level, ii) Community Disaster Profile, iii) Disaster Seasonal Calendar, iv) Proposed interventions for small-scale mitigation measures, livelihood alternative models, v) Messages for IEC materials, early warning system... ) of local communities to natural disaster and climate change risks and recommendations on building the resilience for local communities in the short and long term, which are baseline data for further interventions

Assignment #2:

To design and deliver ToT training for teacher/education staffs on CF DRR-CCA; support education staff/teacher to conduct HVCA and develop Disaster Preparedness Plan (DPP) for elementary and secondary schools in 3 districts

This activity aims at providing primary and secondary school teachers in the target districts with a set of necessary skills and knowledge to facilitate DRR-CCA teaching activities at school.

Trainings topics: facilitation and planning skills, Climate Change Adaptation and Disaster Risk Reduction Knowledge, school preparedness planning skills etc. ToT training should be started with teachers, education staff from city, district levels downwards; more detailed consultation and discussion with Hai Phong City DOET to identify the detailed needs as well as implementation modalities.

Assignment #3:

To conduct researches on the existing status of SMEs in three districts towards DRR-CCA, training needs and CSR; to design and deliver the training to SMEs and related institutions.

Expected results of these exercises are Hai Phong SMEs’ vulnerabilities to disaster risk, climate change; SMEs’ needs, willingness and existing capacities in planning and implementing DRR-CCA activities for their companies/enterprises; the roles and capacities of relevant stakeholders such as local authorities, communities in supporting SMEs to build their resilience towards DR-CC risks [viability of Public-Private Partnership in DRR-CCA]; SMEs’ CSR…

The findings will be inputs for other activities in the both Output 1.1 and 1.3, as well as addressing need for baseline survey of the Outcome 1.

Assignment #4:

To conduct further studies on adaptive livelihood options;

Based on HVCA findings above, in-depth studies on adaptive livelihood options, including access to market, value chain… of the target districts will be undertaken. The expected outcomes of these studies (may be split into different batches) are recommendations for adaptive livelihood options, which may vary from new crop seeds, breeds; new production, post-harvest, value added techniques… to other alternative income opportunities.

Methodologies for deployment of these new opportunities such as how to set up interest groups, how to provide technical training/support, other support modalities from HRCD Project, other sources…should also be elaborated to the extent possible

Specific objectives/expected output and time frame required shall be mentioned in the attached Annex.

- Eligibility criteria

The Consultancy service will be allowed to propose for all or a separated Assignment depending on its compliance to the requirements. The proposal should be indicated clearly of Assignment Number # they are applying for.

The technical proposal must indicate the methodology and output of the assignments while the financial proposal must be based on the time frame and schedule. Except from the consultancy fee, WVV will finance the traveling and accommodation cost of the consultant during consultancy implementation process. The consultant will finance self cost for meals.

The PMT (project management team) of WVV in collaboration with local partners will coordinate necessary logistic arrangements/procedures during the process to enable the consultant to undertake his tasks successfully.

Based on the compliance of the service, WVV will reserve the right to select the most suitable one for a full or for each Assignment.

Desired skills, qualifications, and experience:

The consultant (s) or consulting agency must fulfill the following:

- Advanced degree (Masters or Ph.D.)

- At least 5 years experience in DRR/M, CCA, HVCA and resilience programs with Community Based and/or Child Focus and/or SMEs Focus depending on the specific requirement of each assignment.

- Previous experience on designing and conducting ToT training in related fields for relevant stakeholders.

- Previous experience in participatory research methodologies both qualitative and quantitative.

- Good skills of working with children and vulnerable people

- Proven excellent strategic thinking, participatory approach and analytical skills

- Proven communication and writing skills, including relevant reports

- Proven track record in the related consultancy work

Interested consultants/agencies please study the details in this TOR and attached Annex, send proposal, CV and application letter stating experience and motivation to apply to the email address:  job_application@wvi.org or contact:

People and Culture Department

World Vision International - Vietnam

Address: 4th floor, the HEAC building, 14-16 Ham Long street, Hanoi

Tel: 04. 39439920 (ext.114)

If proposal is sent via post, it is the responsibility of the consultant to ensure postal arriving WVV office before mentioned deadline. Proposals submitted after this deadline will not be considered. Only short-listed candidates will be contacted for interview.

Deadline for application: 20 June 2014

We give equal opportunity to every candidate, regardless of religion, race and gender.

World Vision is a Christian humanitarian organization which works to improve the quality of life of people, especially children, who are marginalized and living in poverty regardless of religion, race and gender.

Glossary

CBDRR/M		Community Based Disaster Risk Reduction/ Mitigation

CCA			Climate Change Adaptation

CF DRR-CCA		Child-Focused Disaster Risk Reduction/Climate Change Adaptation

(C)DPP			(Community) Disaster Preparedness Plan

CDRI			Climate Disaster Resilience Index

CSR			Corporate Social Responsibility

DRR			Disaster Risk Reduction

(H)VCA			(Hazard) Vulnerability Capacity Assessment

PMT			Project Management Team (WVV’s staff)

POA			Plan of Action

PPP			Public-Private Partnership

SME			Small and Medium-sized Enterprises

VCCI			Vietnam Chamber for Commerce & Industry

SDRRP                     	School-based Disaster Risk Reduction Plan

ToT			Training of Trainers

WVV			World Vision Vietnam

ANNEX: DETAIL TOR FOR TOT TRAINING ON CBDRM, CCA & HVCA OF HRCD FOR FY 2014